# American Rescue Plan Act (ARPA) Nevada County Funding Request

Outdoor visitor safety FUND: 
south yuba citizens league-Golden Quartz Picnic Area

| # Operational Priority: | # ☐ 1: Essential # ☒ 2: High-Impact # ☐ 3: Nice to Have | # Timing Priority: | # ☒ 1: Urgent # ☐ 2: 6 months – 1 year # ☐ 3: 1 – 2 years # ☐ 4: Long-term |
| --- | --- | --- | --- |
| # Total Project Budget: | # $46,371 | # ARPA Funding Request: | # $46,371 |
| # ☐ Yes ☒ No Is there FEMA, State or other Direct or Grant Funding available? If Yes, please Specify below |  |  |  |
| # Other Funding Source: |  | # Other Source Amount: |  |
| # Other Funding Source: |  | # Other Source Amount: |  |

# Other FUNDING INFORMATION

N/A

# Project Description

The Outdoor Visitor Safety Fund grant program was established and approved by the Board of Supervisors in April 2021 to provide up to $450,000 in one-time grants from ARPA funds to respond to the negative economic impacts of COVID-19 through promoting public health and safety at highly impacted outdoor recreation destinations. The program offered project funding up to $200,000 for eligible entities including non-profits, businesses, and special districts.  Projects were selected through a competitive process and additional consideration was given to those that support economic development, enhance equitable access, address climate change adaptation, and promote environmental sustainability and resilience. Nine projects were reviewed and approved for a total of $415,570 in funding, and agreements approved by the Board on June 28, 2022, including this project outlined below:

- South Yuba River Citizen’s League (SYRCL) - $46,371 for the installation of a double vault toilet at the Golden Quartz Day Use picnic area.

General Purpose, Focus, and Outcomes Report

☐ 	Mitigate financial hardship, such as declines in revenues due to impacts of periods of business closures, and/or suspended business activities such as revenue generating fund raisers due to social distancing requirements or other public health orders;

☐ 	Support for normal operating costs, including payroll and benefit costs, costs to retain employees, mortgage, rent, or utilities costs, and other operating costs;

☒ 	Support for programmatic services that assist in addressing the economic hardship experienced by the Grant Recipient and/or the negative economic impacts experienced by its customers; and

☐ 	Implementation of COVID-19 prevention or mitigation tactics, such as physical plant changes to enable social distancing, enhanced cleaning efforts, barriers, or partitions, etc.

# NEXUS TO ARPA GUIDELINES

| # ARPA Reporting Category (from US Treasury Reporting Guidance, Appendix 1 – see pages 3-5 below): |  |
| --- | --- |
| # ☒ 1 – Public Health | # ☒ 2 – Negative Economic Impacts |  |
| # ☐ 3 – Public Health – Negative Impact: Public Sector Capacity | # ☒ 5 – Infrastructure |
| # ☐ 6 – Provision of Government Services (Revenue Replacement) | # ☐ 7 – Administrative |
| # Sub-Category (from US Treasury Reporting Guidance, Appendix 1 – see pages 3-5 below): |  |
| # Please provide one Sub-Category designation: 22 |  |

The grants, funded by the American Rescue Plan Act (ARPA), respond to the negative economic impacts of the COVID-19 pandemic with projects to increase resiliency and promote health and safety at highly impacted outdoor recreation destinations. SYRCL is a non-profit organization based in Nevada County, CA.

# NEXUS TO BOARD OBJECTIVES & COUNTY PRIORITIES / COMMUNITY IMPACT

| Board Objectives (select any that apply) |  |  |  |
| --- | --- | --- | --- |
| ☐ Fiscal Stability/Core Svcs. | ☐ Emergency Prep. | ☐ Economic Dev | ☐ Broadband |
| ☐ Cannabis | ☐ Housing | ☐ Homelessness | ☒ Recreation |

| County Priorities (select any that apply) |  |  |
| --- | --- | --- |
| ☐ Costs related to COVID-19 response | ☒ Encourage economic recovery | ☒ Provide long-term benefits to County |

This project intersects with the Board’s Recreation Objective by promoting health and safety at river crossings, lakes, trailheads and other high-use or high-risk destinations. This project promotes health and safety and access through improved infrastructure at impacted recreation destinations.

# OPERATIONAL IMPACT

Will the funds be used to pay for a direct county cost or cost incurred by others? ☐ County Cost ☒ Other Cost

# Project Timeline / Readiness

| Grant award agreement executed: | 6/28/22 |
| --- | --- |
| First quarterly report received: | Received, 9/12/22 |
| Second quarterly report received: | Received, 1/17/23 |
| Third quarterly report received: | Received, 4/10/23 |
| Fourth quarterly report received: | Received, 7/6/23 |
| Fifth quarterly report received: | Received, 10/9/23 |
| Project Completed: | In progress |

# BUDGET DETAIL

In what SBU/Office 2/Account(s) will ARPA-funded project activity be incurred?

| SBU | Ofc2 | Account | Amount | Description |
| --- | --- | --- | --- | --- |
| 70102 | 325 | 521520 | 46,371 | Outdoor Visitor Safety Fund |
| Total |  |  | $46,371 | Note: Total should match ARPA Funding Request amount |

EXPENDITURE TRACKING/REPORTING

Total expenditures as of 10/5/2023: $1,097.01

Nevada County made 1st of 2 payments totaling: $34,778

Project Narrative:

| First quarterly report | June – August 2022 | The vault toilets have been ordered; purchase agreement was provided from Boom Concrete, Inc. |
| --- | --- | --- |
| Second quarterly report | Sept – December 2022 | During this period, staff time was spent on coordination with the USFS and Boom Concrete. The double vault toilets were originally slated for installation before Oct. 15, 2022. Unfortunately supply chain and staffing shortage issues at Boom pushed estimated installation date to spring 2023. Snow at the installation site may warrant waiting until June. SYRCL will continue to work with USFS to determine timing in coordination with Boom. |
| Third quarterly report | Jan – March 2023 | The USFS has conducted a site visit of the Golden Quartz Day Use area and reports that it is accessible and drying out quickly from the recent snow. The USFS also reports that they continue to be in touch with Boom Toilets in order to finalize the delivery date for the vault restrooms. Boom is located in South Dakota and indicates they’re planning for the end of June for their California delivery trip. Timeline updates are expected at the end of April. |
| Fourth quarterly report | April – June 2023 | Project has been delayed. The vault restroom delivery Is anticipated to take place at the end of July to early August. |
| Fifth quarterly report | July-September 2023 | Boom Toilets attempted their delivery of the vault restrooms in July but was unsuccessful due to road conditions. The new delivery date, according to the US Forest Service, is October 12-14, 2023. |

# Project Point of Contact

# Name and title: Erika Seward, Sr. Administrative Analyst - CDA

FOR CEO OFFICE ONLY:

| Expense Item No: | x |
| --- | --- |
| Final ARPA Category: | x |
| Approved: | ☒ Yes ☐ No |