# American Rescue Plan Act (ARPA) Nevada County Funding Request

Outdoor visitor safety fund: bEAR yUBA lAND TRUST
ADAM RYAN PRESERVE PArking Improvements

| # Operational Priority: | # ☐ 1: Essential # ☒ 2: High-Impact # ☐ 3: Nice to Have | # Timing Priority: | # ☒ 1: Urgent # ☐ 2: 6 months – 1 year # ☐ 3: 1 – 2 years # ☐ 4: Long-term |
| --- | --- | --- | --- |
| # Total Project Budget: | # $99,500 | # ARPA Funding Request: | # $99,500 |
| # ☐ Yes ☒ No Is there FEMA, State or other Direct or Grant Funding available? If Yes, please Specify below |  |  |  |
| # Other Funding Source: |  | # Other Source Amount: |  |
| # Other Funding Source: |  | # Other Source Amount: |  |

# Other FUNDING INFORMATION

N/A

# Project Description

The Outdoor Visitor Safety Fund grant program was established and approved by the Board of Supervisors in April 2021 to provide up to $450,000 in one-time grants from ARPA funds to respond to the negative economic impacts of COVID-19 through promoting public health and safety at highly impacted outdoor recreation destinations. The program offered project funding up to $200,000 for eligible entities including non-profits, businesses, and special districts.  Projects were selected through a competitive process and additional consideration was given to those that support economic development, enhance equitable access, address climate change adaptation, and promote environmental sustainability and resilience. Nine projects were reviewed and approved for a total of $415,570 in funding, and agreements approved by the Board on June 28, 2022, including this project outlined below:

- Bear Yuba Land Trust (BYLT) - $99,500 for parking improvements to the Adam Ryan Preserve Trailhead.

General Purpose, Focus, and Outcomes Report

☐ 	Mitigate financial hardship, such as declines in revenues due to impacts of periods of business closures, and/or suspended business activities such as revenue generating fund raisers due to social distancing requirements or other public health orders;

☐ 	Support for normal operating costs, including payroll and benefit costs, costs to retain employees, mortgage, rent, or utilities costs, and other operating costs;

☒ 	Support for programmatic services that assist in addressing the economic hardship experienced by the Grant Recipient and/or the negative economic impacts experienced by its customers; and

☐ 	Implementation of COVID-19 prevention or mitigation tactics, such as physical plant changes to enable social distancing, enhanced cleaning efforts, barriers, or partitions, etc.

# NEXUS TO ARPA GUIDELINES

| # ARPA Reporting Category (from US Treasury Reporting Guidance, Appendix 1 – see pages 3-5 below): |  |
| --- | --- |
| # ☒ 1 – Public Health | # ☐ 2 – Negative Economic Impacts |  |
| # ☐ 3 – Public Health – Negative Impact: Public Sector Capacity | # ☒ 5 – Infrastructure |
| # ☐ 6 – Provision of Government Services (Revenue Replacement) | # ☐ 7 – Administrative |
| # Sub-Category (from US Treasury Reporting Guidance, Appendix 1 – see pages 3-5 below): |  |
| # Please provide one Sub-Category designation: 22 |  |

The grants, funded by the American Rescue Plan Act (ARPA), respond to the negative economic impacts of the COVID-19 pandemic with projects to increase resiliency and promote health and safety at highly impacted outdoor recreation destinations. BYLT is a non-profit based in Nevada County, CA

# NEXUS TO BOARD OBJECTIVES & COUNTY PRIORITIES / COMMUNITY IMPACT

| Board Objectives (select any that apply) |  |  |  |
| --- | --- | --- | --- |
| ☐ Fiscal Stability/Core Svcs. | ☐ Emergency Prep. | ☐ Economic Dev | ☐ Broadband |
| ☐ Cannabis | ☐ Housing | ☐ Homelessness | ☒ Recreation |

| County Priorities (select any that apply) |  |  |
| --- | --- | --- |
| ☐ Costs related to COVID-19 response | ☒ Encourage economic recovery | ☒ Provide long-term benefits to County |

This project intersects with the Board’s Recreation Objective by promoting health and safety at river crossings, lakes, trailheads and other high-use or high-risk destinations. This project promotes health and safety and access through improved infrastructure at impacted recreation destinations.

# OPERATIONAL IMPACT

Will the funds be used to pay for a direct county cost or cost incurred by others? ☐ County Cost ☒ Other Cost

# Project Timeline / Readiness

| Grant award agreement executed: | 6/28/22 |
| --- | --- |
| First quarterly report received: | Received, 9/7/22 |
| Second quarterly report received: | Received, 1/17/23 |
| Third quarterly report received: | Received, 4/21/23 |
| Fourth quarterly report received: | Received, 7/12/23 |
| Fifth quarterly report received: | Received:10/13/23 |
| Sixth quarterly report received: | Received: 1/11/24 |
| Seventh quarterly report received: | Received: 12/31/2024 |

# BUDGET DETAIL

In what SBU/Office 2/Account(s) will ARPA-funded project activity be incurred?

| SBU | Ofc2 | Account | Amount | Description |
| --- | --- | --- | --- | --- |
| 70102 | 325 | 521520 | 99,500 | Outdoor Visitor Safety Fund |
| Total |  |  | $99,500 | Note: Total should match ARPA Funding Request amount |

EXPENDITURE TRACKING/REPORTING

Total expenditures as of 12/22/2023: $102,674.55

Nevada County has made 2nd of 2 payments totaling $99,500

Project Narrative:

| First quarterly report | June – Aug 2022 | We have just begun further planning efforts; a rendering of the parking lot was created which will be provided to the County for guidance before engaging an engineer to design. |
| --- | --- | --- |
| Second quarterly report | Sept – Dec 2022 | BYLT Staff is working with Bill Green and Nevada City Engineering to create a map of the location where the parking lot will be located. The map will show where material will be excavated and where fill is needed. Calculations for volume will be included and we will take this map to Hansen Bros, C&D Construction and other contractors for bids. |
| Third quarterly report | Jan – March 2023 | A detailed site plan from Nevada City Engineering was completed; we submitted plans to the building department with three items that need to be address (permit #230872); when the permit is ready to be issued, an encroachment permit will be required. |
| Fourth quarterly report | April – June 2023 | BYLT staff and Bill Green worked together to create an RFP for the project. The RFP has been shared with contracting firms and we are accepting bids until July 28th. Once all the submissions are in they will be reviewed and then we will decide which company gets the job by August 11th. We will have the project completed by 12/31/23. |
| Fifth quarterly report | July-September 2023 | BYLT staff and Bill Green worked together to evaluate the proposals received based on the RFP we created. The job was offered to Glen Grennon and Sons. They have been making progress on the grading and site preparation and are near completion. They removed the existing fence surrounding the old parking lot. BYLT will hire a company to install a new fence once the parking lot project is completed. We have already solicited bids. BYLT will complete the erosion control measures outlined by the County in the building permit. Glen Grennon is planning on doing the paving next week (10/16-10/20). We will have the project completed by 12/31/23 |
| Sixth quarterly report | October-December 2023 | The project is nearly complete; however there is some discussion with the Nevada County Building Department on meeting code requirements. |
| Seventh quarterly report | January – March 2024 | The project is nearly complete; however there is some discussion with the Nevada County Building Department on meeting code requirements. Likely we will need to address this issue. |

# Project Point of Contact

# Name and title: Erika Seward, Sr. Administrative Analyst - CDA

FOR CEO OFFICE ONLY:

| Expense Item No: | x |
| --- | --- |
| Final ARPA Category: | x |
| Approved: | ☒ Yes ☐ No |